Charter School Planning Grant Preparation Spread Sheet

Developed by Holly Hart (www.hollyhartconsulting.com) January 2010

(Check for changes on application forms for subsequent years)

| ACTIVITY | RESPONSIBLE PERSON(S) | START DATE | DATE COMPLETED | NOTES/CONCERNS |
| --- | --- | --- | --- | --- |
| Generate the idea |  |  |  |  |
| Begin and document the planning process |  |  |  | Document dates, members, activities, tasks |
| Add members to the planning committee |  |  |  | Parents, community members, staff, etc. |
| Determine the type of school/curricular focus/methodology |  |  |  |  |
| Determine ages and grade levels to be served |  |  |  |  |
| Develop the mission statement |  |  |  |  |
| Write a vision statement |  |  |  | Consistent with mission statement |
| Develop/write belief and value statements |  |  |  | Consistent with mission and values |
| Develop the goals for the school |  |  |  | Measureable and for each of three years |
| Develop the goals for the grant |  |  |  | Measureable and for each of three years |
| Determine level of authorizer interest/support |  |  |  | Secure board motion in support of school |
| Determine the curriculum and instructional practices and supporting research |  |  |  | Utilize PBL (Project Based Learning), Green and other networks |
| Determine the level of community support |  |  |  |  |
| Determine and articulate the philosophy of the school |  |  |  |  |
| Identify the innovations to be attempted |  |  |  |  |
| Determine why you need a charter school |  |  |  |  |
| Determine the initial enrollment target and five year enrollment and staffing projections |  |  |  |  |
| Develop a 5 year strategic plan |  |  |  |  |
| Develop 5 year budget projections |  |  |  | Use DPI forms in grant application |
| Identify the instructional and non-instructional staff needed and skills needed by staff |  |  |  |  |
| Develop a staff development plan |  |  |  | For four years |
| Identify potential training/trainers |  |  |  |  |
| Develop a governance board recruitment and training plan |  |  |  |  |
| Determine methods/types of student assessments |  |  |  | Assessment should document individual student gains/improvement |
| Determine a school evaluation plan |  |  |  |  |
| Develop an MOU (Memorandum of Understanding) with each union |  |  |  | Three way agreements between the charter school governance board, school board and union are recommended |
| Establish the governance board |  |  |  |  |
| Establish the 501c3 non-stock corporation and by laws |  |  |  | If choosing to use the 501c3 non-profit corporation structure |
| Determine governance process consistent with by laws |  |  |  |  |
| Secure IRS number |  |  |  | If using the 501c3 non-profit corporation structure |
| Select an administrator or establish the selection process |  |  |  |  |
| Determine needed waivers/exemptions from state laws and district policies |  |  |  | A statement in the contract allowing the governance board to exempt the school from authorizer’s policies inconsistent with the school’ mission is recommended |
| Plan implementation processes |  |  |  | Parents must be included |
| Determine facility needs and facility location |  |  |  |  |
| Determine who will provide SPED (Special Education and ELL (English Language Learner) services |  |  |  | District, CESA, contracted service, charter school |
| Establish the admission process |  |  |  | Including lottery |
| Develop recruitment and publicity plans |  |  |  |  |
| Develop board, school, finance and staff sustainability plans |  |  |  |  |
| Develop charter/contract |  |  |  |  |
| Write, revise, submit grant application |  |  |  |  |